## Yehuan Huang
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
3 | Yehuan Huang | 10 | 8 | 2 | 0 - learning PHP and HTML and Github 1 - requirement analysis 2 - design 5 - attend group meeting | 5 | 1 | 4 | 0 | 0 | 2 | 0 | 20 | 20
4 | Yehuan Huang | 20 | 15 | 5 | 0 - learning PHP and HTML and Github 1 - requirement analysis 2 - UI design 5 - attend group meeting, management of Pivitol Tracker | 5 | 1 | 9 | 0 | 0 | 5 | 0 | 25 | 25
5 | Yehuan Huang | 33 | 25 | 8 | 0- learning php coding html 1- required analysis 2- design 3- Making UI of update_patient 4- basic test 5- group meeting | 10 | 1 | 1 | 12 | 1 | 8 | 0 | 40 | 40

## Wenji Shi
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Wenjie Shi | 8 | 6 | 2 | 0 - learning all tools 1 - requirement analysis 5 - attend group meeting | 4 | 1 |  |  |  | 1 |  | 0 - learning PHP, development tools. 1 - finish some part of SQAP 5 - email 6 - prepare the presentation and set up environment | 12
2 | Wenjie Shi | 12 | 8 | 4 | 0 - learning PHP 1 - finish some parts of SQAP 6 - prepare the presentation | 3 | 2 |  |  |  |  | 3 | 0 - learning PHP. 3 - control (add patients) 5 - email 6 - set up environment | 16
3 | Wenjie Shi | 18 | 12 | 6 | 0 - learning PHP, pivator tracker, github 1 - make sure of control part 3 - practice search control 6 - set up environment | 3 | 1 |  | 6 |  |  | 2 | 0 - learning cakePHP. 1 - figure out patient part. 3 - patient part. 5 - communicate with team members. | 20
4 | Wenjie Shi | 20 | 18 | 2 | 0 - learning cakePHP 1 - figure out patient control part 3 - patient controller first edition 4 - test patient controller part | 6 | 1 |  | 8 | 3 |  |  | 0 - learning cakePHP. 3 -modify patient part. 5 - communicate with UI and model part. | 15
5 | Wenjie Shi | 12 | 9 | 3 | 0 - learning cakePHP 3 - patient controller is compatible with UI 4 - test 5 - communication with UI part | 2 |  |  | 5 | 1 | 1 |  | 0 - learning cakePHP. 3 - finish patient part. 4 - test patient part. | 10

## Jeff Andre
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Jeff Andre | 10 | 8 | 2 | Task Breakdown 0 - learning and installing git 1 - requirement analysis 5 - communication/management, 6 - documentation | 1 | 4 |  |  |  | 2 | 1 | 0 - learn local environment, 1- requirements, 5 - SPMP | 10
2 | Jeff Andre | 19 | 15 | 4 | Task Breakdown 0 - learing pivitol tracker & PHP 1 - requirements and estimates in pivitol tracker 2 - review wireframe, algorithm, architecture 3 - 4 - 5 - management 6 - SPMP | 2 | 3 | 5 |  |  | 1 | 4 | 1 - requirements, 2 - design, 5 - comm/mgt | 10
3 | Jeff Andre | 16 | 11 | 5 | Task Breakdown 0 - attended Jason's demo on Git and cake PHP, viewed cakePHP tutorials 1 - reviewed wireframe with customer 2 - architecture with cakePHP framework 3 - 4 - 5 - management, assignments and estimates in pivitol tracker 6 - | 4 | 3 | 2 |  |  | 2 |  |  | 10
4 | Jeff Andre | 16 | 14 | 2 | Task Breakdown 0 - 1 - reviewed algorithm with customer 2 - 3 - implemented algorithm 4 - Tested algorithm and main web page 5 - followed up on team status and action items 6 - updated SPMP |  | 1 |  | 8 | 2 | 2 | 1 | - presentation, algorithm implementation, testing web site | 15
5 | Jeff Andre | 19 | 16 | 3 | Task Breakdown 0 - 1 - reviewed algorithm and web site with customer 2 - 3 - updated algorithm 4 - Tested algorithm and web pages for 1st iteration 5 - following up on action items, updating pivotal tracker 6 - Presentation for iteration 1 |  | 1 |  | 1 | 8 | 2 | 4 | - integrate algorithm with system, management, testing | 15

## Jason Lu
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Jason Lu | 10 | 8 | 2 | Task Breakdown 3 - Setup GitHub repo. 3 - Setup local environments. 0 - Survey Twitter Bootstrap CSS 3.0 0 - Survey PHP frameworks | 3 | 0 | 0 | 5 | 0 | 0 | 0 | 3 - Basic infrastructure of MVP 3 - Deployment script | 8
2 | Jason Lu | 15 | 13 | 2 | 0 - Play with CakePHP 0 - Play with Bootstrap 3.0 3 - Deploy script 3 - Work on basic structure of project 1 - Meeting with Professor Guanglan Zhang (The Customer) 5 - Prepare for git tutorial. | 4 | 2 | 0 | 6 | 0 | 3 | 0 | 6 - Give team git tutorial 6 - Give team MVC tutorial 3 - Setup team members' working env. 3 - Work on user management funcs. | 12
3 | Jason Lu | 17 | 11 | 6 | 5 - Give git & CakePHP tutorial 3 - User controller, add CRUD actions. 3 - User view, basic view (no design) in order to work on controller 0 - Study Solr (Full text search server) to see if it fit for us in future iterations | 2 | 0 | 0 | 3 | 0 | 6 | 0 | 2 - Find a way for DB migration 5 - Help team for implementation | 6
4 | Jason Lu | 10 | 7 | 3 | 3 - User controller - registraion action 0 - Study Solr (Full text search server) 5 - Help team for implementation | 2 | 0 | 0 | 2 | 0 | 3 | 0 | 5 - Help team for implementation | 6
5 | Jason Lu | 11 | 7 | 4 | 3 - Structure refactor, rename some methods to avoid term conflict. 3 - Patient update method fix, 0 - Study Solr (Full text search server) 5 - Help team for implementation | 2 | 0 | 0 | 2 | 0 | 3 | 0 | 5 - Help team for implementation | 6

## Yike Xue
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Yike Xue | 7 | 4 | 3 | Task Breakdown 0 - learning 1 - requirement analysis 5 - communication/management | 2 | 1 |  |  |  | 1 |  | 0- learning PHP and database 1 - write the SQAP and analyze the user requirements 5 - communication with group members and prepare for the first presentation 6 - set up the working environment and github account | 8
2 | Yike Xue | 12 | 8 | 4 | Task Breakdown 0 - learning PHP and how to use tools(GitHub, Pivotal) 1 - requirement analysis (SQAP) 5 - communication/management (prepare for the presentation) | 2 | 5 |  |  |  | 1 |  | 1 - update the SQAP 2 - database design 5 - communication/management 6 - algorithm analysis | 8
3 | Yike Xue | 9 | 5 | 4 | Task Breakdown 0 - learning PHP and some algorithm 2 - database design( focus on patient table, visit table, and user table and their relationship) 3 - implementation(model: patient and visit, including some functions in the patient model) | 1 | 2 |  | 2 |  |  |  | 0 - learning algorithm 1 - requirement analysis (modifying the SQAP) 2 - database design (modified the former one) 3 - implementation( update the models of some new tables or modified tables) | 10
4 | Yike Xue | 8 | 6 | 2 | Task Breakdown 1 - requirement analysis (modifying the SQAP) 2 - database design (modified the former one) 3 - implementation( update the models of some new tables or modified tables) |  | 1 | 2 | 3 |  |  |  | 0 - learning algorithm and cakePHP 1 - requirement analysis (do coding lines statistics) 3 - implementation( update the models of some new tables or modified tables) | 8
5 | Yike Xue | 5 | 4 | 1 | Task Breakdown 0 - learning (cakePHP) 1 - requirement analysis (do coding lines statistics) 3 - implementation( update the vital_labs model and modified patient model) |  | 1 | 1 |  | 2 |  |  | 0 - learning algorithm and cakePHP 1 - requirement analysis (do coding lines statistics) 3 - implementation( update the models of some new tables or modified tables) | 8

## Yingyuan Zhang
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Yingyuan Zhang | 10 | 8 | 2 | Task Breakdown 0 - reading project documents 0 - learning PHP 0 - creating GitHub account 1 - requirement analysis 5 - emailing Prof.Zhang and team leader Jeff to apply for joining this group | 4 | 2 | 0 | 0 | 0 | 2 | 0 | 0 - learning PHP 3 - creating Pivotal Tracker account and inviting other group members 3 - install PHP, MySQL, and APACHE 1 - requirement analysis 5 - meeting customers 5 - attending group meeting | 12
2 | Yingyuan Zhang | 12 | 8 | 4 | 0 - learning Pivitol Tracker and PHP 1 - requirement analysis 3 - creating Pivotal Tracker account, inviting other group members, and managing it 3 - setup local enviroments(APACHE, MySQL, PHP) 5 - meeting customer(Professor Zhang, Guanglan) 5 - attending group meeting | 4.5 | 1 | 0 | 2.5 | 0 | 4 | 0 | 0 - learning Pivitol Tracker and PHP 2 - design UI or DB 3 - implement UI or DB 5 - manage Pivotal Tracker 5 - attending group meeting | 12
3 | Yingyuan Zhang | 14.5 | 8.5 | 6 | 0 - learning GitHub, Pivitol Tracker, and PHP 3 - setup local enviroments(IDE) 3 - practice the implementation of PHP controller 5 - management of Pivitol Tracker 5 - attending group meeting | 5.5 | 0 | 0 | 3 | 0 | 6 | 0 | 0 - learning PHP(cakePHP tutorials) 3 - practice the implementation of VisitsController 3 - help implementing PatientsController 5 - management of Pivotal Tracker 5 - attending group meeting | 14
4 | Yingyuan Zhang | 13 | 11 | 2 | 0 - learning PHP(cakePHP tutorials) 3 - implement VisitsController (version_1) 5 - management of Pivotal Tracker 5 - attending group meeting | 10 | 0 | 0 | 1 | 0 | 2 | 0 | 0 - learning PHP 2 - design Visit page 3 - mainly implement add( ) and view( ) of VisitsController (version_2) 5 - management of Pivotal Tracker 5 - attending group meeting | 14
5 | Yingyuan Zhang | 15 | 13 | 3 | 0 - learning PHP 2 - design add Visit page 3 - mainly implement add( ) and view( ) of VisitsController (version_2) 5 - attending group meeting | 3.5 | 0 | 0.5 | 8 |  | 3

## Maura
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Maura | 7 | 5 | 2 | 0 - learning (Git, GitHub, PHP, D3 library for visualization, CakePHP, refreshing on CSS, HTML, Twitter Bootstrap) 1 - requirement analysis (reviewed project requirements and spent time on basic understanding of project domain) 3 - implementation (setup Git and GitHub account and sent setup steps to rest of group) | 2 | 2 | 0 | 1 | 0 | 0 | 0 | 0 - learning (continuing learning PHP and Twitter Bootstrap) 1 - requirement analysis (set up Pivotal Tracker account and become familiar with environment) 2 - design (wireframes, user stories) 5 - communication/management (group meeting and emailing) 6 - unclassified (review presentation) | 10
2 | Maura | 10 | 8 | 2 | 0 - learning (Pivotal Tracker, PHP, CakePHP framework, MVC refreshing) 1 - requirement analysis 2 - design (wireframes, reviewing bootstrap design and D3 graph potential) 3 - implementation(setting up Pivotal Tracker account, local dev environment) 5 - communication/management 6 - unclassified (help edit SPMP) | 2 | 0.5 | 3 | 1 |  | 3 | 0.5 | 0 - learning (dev tools and continue with PHP) 1 - requirement analysis (user stories pivotal tracker) 2 - design (continue UI design and brainstorming, begin UI dev) 3 - implementation 5 - communication/management (email and group meeting) | 12
3 | Maura | 10 | 7 | 3 | 0 - learning (cakephp, php) 1 - requirement analysis (running and reviewing current committed code) 3 - implementation (setting up development environment and getting existing code to run properly, downloaded and installed xampp and mysql) 5 - communication/management (group meetings, email communication) | 4 | 1 |  | 2 |  | 3 |  | 0 - learning 2 - design (meet with UI group to finish designs and ui gameplan, make, finish development of views adn commit to github) 3 - implementation (finish setting up environment and review with Jason to make sure running properly) 5 - communication/management (team meetings, individual ui meeting, email communication) | 15
4 | Maura | 14 | 10 | 4 | 0 - learning(learning cakephp, php while developing the views) 1 - requirement analysis(reviewed user requirements for ui) 3 - implementation (set up default.ctp, the welcome page, search page, worked on search controller, integrated everything with the new database to be able to search patients correctly) 5 - communication/management (group meetings) | 1 | 1 |  | 8 |  | 4 |  | 0 -learning (continuing to learn all technologies) 1 - requirement analysis (make sure ui aligns with user requirements) 2 - design(design rest of ui screens) 3 - implementation (continuing development) 4 - test(test all pages and controllers to make sure integrating appropriately) 5 - communication/management(team meetings)

## Bogdan
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Bogdan | 7 | 5 | 2 | Task Breakdown 0 - learning (Git/GitHub) 1 - requirement analysis 5 - communication/management 6 - PM documentation | 0.5 | 1 | 0 | 0 | 0 | 0.5 | 3 | Task Breakdown 0 - learning (Deveolpment Tools) 1 - requirement analysis (Pivotal Tracker) 2 - design (Wireframes, Database) 5 - communication/management 6 - SPMP, 1/3 of Projects presentation, reading and analysing medical algorithm | 12
2 | Bogdan | 15.5 | 11.5 | 4 | Task Breakdown 0 - learning (Software for wireframes, PHP) 1 - requirement analysis 2 - design (Wireframes) 5 - communication/management 6 - SPMP, Presentation | 1 | 1 | 5 | 0 | 0 | 0.5 | 4 | Task Breakdown 0 - learning (Deveolpment Tools, PHP) 1 - requirement analysis 2 - design (Database) 5 - communication/management 6 - analysing of medical algorithm 3 - implementation (database) 4 - test (database) | 15
3 | Bogdan | 19 | 14 | 5 | Task Breakdown 0 - learning (CakePHP) 1 - requirement analysis 2 - design (Database) 5 - communication/management 6 - unclassified (algorithm analysis) | 1 | 1 | 10 | 0 | 0 | 1 | 1 | Task Breakdown 0 - learning (CakePHP) 1 - requirement analysis 2 - design (UI) 3 - implementation(Database, UI) 4 - test(Database, UI) 5 - communication/management 6 - unclassified (meeting with customers) | 15
4 | Bogdan | 19 | 17 | 2 | Task Breakdown 0 - learning (CakePHP) 1 - requirement analysis 2 - design (Database, UI for database testing) 3 - implementation (Database) 4 - test (Database) 5 - communication/management | 5 | 1 | 6 | 2 | 2 | 1 | 0 | Task Breakdown 0 - learning (CakePHP) 1 - requirement analysis (customer feedback) 2 - design (UI, algorithm) 3 - implementation(UI, algorithm) 4 - test(Database, UI) 5 - communication/management 6 - unclassified (class presentation #2) | 15
5 | Bogdan | 7.5 | 5.5 | 2 | Task Breakdown 0 - learning (CakePHP) 1 - requirement analysis (customer feedback) 4 - test (Database) 5 - communication/management 6 - unclassified (Presentation) | 3 | 0.5 | 0 | 0 | 0.5 | 1 | 0.5 | Task Breakdown 0 - learning (CakePHP) 1 - requirement analysis (customer feedback) 2 - design (patient visit) 3 - implementation(patient visit) 4 - test (patient visit) 5 - communication/management 6 - unclassified (update documentation) | 15
6 | Bogdan

## Yulu
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Yulu | 9 | 7 | 2 | 0 - learning learning Git and Github using Database Algorithm CSS HTML knowledge review 1 - requirement analysis Project document reading and understanding | 4 | 3 | 0 | 0 | 0 |  | 0
2 | Yulu | 12 | 8 | 4 | 0-learn PHP 1-requirment analysic 3-setting local XAMPP, Apache, MySQL and play with it 6-reganize the meeting minutes and post it afterwards | 5 | 1 |  | 1 |  |  | 1 | 18 (start programming on UI)& team meeting, Indivisual group meeting.
3 | Yulu | 13 | 8 | 5 | 0-learn CakePHP(2) learn PHP Programming (3) 1-read the code we have now 3-fix my enviroment connecting to Github,eg. zend Studio | 5 | 2 |  | 1 |  |  |  | 15
4 | Yulu | 17 | 13 | 4 | 0-learn CakePHP, embedded html in PHP 3-Add Patient VIew Patient Page Programming 5-meet with UI team | 7 |  |  | 6
5 | Yulu |  | 11 |  | 3-Add Patient Modification and VIew Patient(7) fix the user low priority on dbproblem(4)